## Slide 1: Week 1 (21-Apr to 27-Apr) Chris Porter
Goal/Task | % Done | Hours (Act.)
Everyone Complete Leadership Foundation: Clarify Purpose (p. 32-33), Team Purpose Statement (p. 34), Voice Finder (p. 64-67), Your Contribution Statement (p. 68), Win-Win Performance Agreement (p. 76) | 40% | 1.4
Team Complete: Project Objective / Mission Statement (clear and concise, <25 words, see example below) | 100% | 0.​1
Team Complete: Project Task Template (Conditions or tasks that must be completed, work that needs to be done) | 100% | 2.5
Research (Previous work done) | ~50% | 6
Hours on task during the week (On track ≥ (13) / wk) | 10
Total hours on task so far this semester (On track ≥ 13 hrs) | 10
Create a TMR-ed system with various configurations of the RISC-V instruction set on an FPGA to test the possibility of its use in space.

## Slide 2: Progress made during the week (Log) (What I did)
Research on previous work done for project
Aquired PCB Hardware for the team
Team meetings to make decisions about schedule and breaking up tasks

## Slide 3: Difficulties encountered during the week (What I did not do and why)
Leadership Foundation: not enough time worked on the project or with the team to answer all questions accurately or to answer them seriously. Instructions/expectations for the leadership training for this week were vague.
More research needs to be done to be 'caught up to speed' on the project.

## Slide 4: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Learn SoftConsole and Libero | 05/17 | 5
Check Schematics and PCB layout for Accuracy | 05/17 | 5
Full Duplex UART | 06/07 | 3
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 3

## Slide 5: How can we help you achieve your goals?
Admin on STC159L02
Access to STC159L02 and FPGA

## Slide 6
Notes: Taken from Elder Bednar’s address: http://www2.byui.edu/Presentations/Transcripts/Devotionals/2006_10_31_Bednar.htm

## Slide 7: Week 1 (21-Apr to 27-Apr) Jonah Boe
Goal/Task | % Done | Hours (Act.)
Everyone Complete Leadership Foundation: Clarify Purpose (p. 32-33), Team Purpose Statement (p. 34), Voice Finder (p. 64-67), Your Contribution Statement (p. 68), Win-Win Performance Agreement (p. 76) | 100 | 2
Team Complete: Project Objective / Mission Statement (clear and concise, <25 words, see example below) | 100 | 0.1
Team Complete: Project Task Temple (Conditions or tasks that must be completed, work that needs to be done) | 100 | 3
Research PCB assembly options and find solution to VGA problem | 90 | 3
Hours on task during the week (On track ≥ (13) / wk) | 14.1
Total hours on task so far this semester (On track ≥ 13 hrs) | 14.1
Create a TMR-ed system with various configurations of the RISC-V instruction set on an FPGA to test the possibility of its use in space.

## Slide 8: Progress made during the week (Log) (What I did)
Researched options for PCB assembly. Could not find one in the US (this is a problem due to COVID-19). Studied the schematics and board to determine the right tools for assembly. Decided on two 90-degree VGA adapters and two straight VGA adapters in order to solve problem were VGA plugs will not connect due to their proximity on the circuit board. Researched best route for adding to the silk screen by hand over via's at point of the FPGA connection adapter in order to mitigate chance of solder bridging during reflow.

## Slide 9: Difficulties encountered during the week (What I did not do and why)
VGA problems on the PCB
Exposed via's under FPGA connector

## Slide 10: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Order tools and parts in order to solder the board | May 04, 2020 | 2
Obtain a reflow oven, heat gun, and micro camera for soldering | May 01, 2020 | 1
Check status of getting lab computer 01 onto my network | May 01, 2020 | 1
Review schematic for errors (includes determining the origin of the reference schematics used in the design.) | May 04,2020 | 5
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 14

## Slide 11: How can we help you achieve your goals?
I need a reflow oven and heat gun
I need the process of getting the computer out of the STC in the works ASAP

## Slide 12
Notes: Taken from Elder Bednar’s address: http://www2.byui.edu/Presentations/Transcripts/Devotionals/2006_10_31_Bednar.htm

## Slide 13: Week 1 (21-Apr to 27-Apr) Spencer Cheney
Goal/Task | % Done | Hours (Act.)
Everyone Complete Leadership Foundation: Clarify Purpose (p. 32-33), Team Purpose Statement (p. 34), Voice Finder (p. 64-67), Your Contribution Statement (p. 68), Win-Win Performance Agreement (p. 76) | 90% | 1
Team Complete: Project Objective / Mission Statement (clear and concise, <25 words, see example below) | 100% | 0.5
Team Complete: Project Task Temple (Conditions or tasks that must be completed, work that needs to be done) | 100% | 1.5
Hours on task during the week (On track ≥ (13) / wk) | 12
Total hours on task so far this semester (On track ≥ 13 hrs) | 12
Create a TMR-ed system with various configurations of the RISC-V instruction set on an FPGA to test the possibility of its use in space.

## Slide 14: Progress made during the week (Log) (What I did)
For example: Resources found (links, manuals), Designs created, Decisions made and corresponding rational, Photos of prototype progress, etc.
Reviewed previous team's documentation
Became familiar with project and sources

## Slide 15: Difficulties encountered during the week (What I did not do and why)

## Slide 16: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Review Code (specifically UART) | May 11 | 5
Review Schematics | May 4 | 3
Become familiar with tools (SoftConsole) | May 11 | 5
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 17: How can we help you achieve your goals?
It help if we could get the computer out of the STC right away

## Slide 18
Notes: Taken from Elder Bednar’s address: http://www2.byui.edu/Presentations/Transcripts/Devotionals/2006_10_31_Bednar.htm

## Slide 19: Week 1 (21-Apr to 27-Apr) Kyle Tolliver
Goal/Task | % Done | Hours (Act.)
Everyone Complete Leadership Foundation: Clarify Purpose (p. 32-33), Team Purpose Statement (p. 34), Voice Finder (p. 64-67), Your Contribution Statement (p. 68), Win-Win Performance Agreement (p. 76) | 100 | 2.25
Team Complete: Project Objective / Mission Statement (clear and concise, <25 words, see example below) | 100 | .08
Team Complete: Project Task Temple (Conditions or tasks that must be completed, work that needs to be done) | 100 | 2.5
Hours on task during the week (On track ≥ (13) / wk) | 10
Total hours on task so far this semester (On track ≥ 13 hrs) | 10
Create a TMR-ed system with various configurations of the RISC-V instruction set on an FPGA to test the possibility of its use in space.

## Slide 20: Progress made during the week (Log) (What I did)
For example: Resources found (links, manuals), Designs created, Decisions made and corresponding rational, Photos of prototype progress, etc.
Look through past semester work
Tasks sheet and Proposal
Download SoftConsole
Worked with Zac to clearify questions

## Slide 21: Difficulties encountered during the week (What I did not do and why)
PCB Errors
Left Arduino in Rexburg

## Slide 22: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Get Arduino | Friday | .25
Test Arduino | Saturday | 1
SPI/I2C on Arduino | May 17 | 10
Leadership | May 4 | 2.5
Class | Thursday | 6
Review Past Semester | May 4 | 5
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 23: How can we help you achieve your goals?
Clarify Leadership workbook
Clarify purchasing card sign form
Information about the computer in the lab

## Slide 24
Notes: Taken from Elder Bednar’s address: http://www2.byui.edu/Presentations/Transcripts/Devotionals/2006_10_31_Bednar.htm