## Slide 1: Week 4 (28-Apr to 4-May) Chris Porter
Goal/Task | % Done | Hours (Act.)
Learn SoftConsole and Libero | 15% | 2
Check Schematics and PCB Layout for Accuracy/Workability | 90% | 3.33
Meetings |  | 1.83
Leadership Training | 18% | 1
UART | 0% | 0
Hours on task during the week (On track ≥ 13 / wk) | 8.16
Total hours on task so far this semester (On track ≥ 26 hrs) | 18.17

## Slide 2: Progress made during the week (Log) (What I did)
Schematics:
  Accelerometer set up for I2C, but documentation states it's set up for SPI. Schematic/PCB looks correct.
  Barometer is correct, R22 and R23 are pull up resistors for a couple ICs, documentation not clear.
  TODO: Clean up Documentation?
Installed SoftConsole, 30 minute tutorial on Libero/Softconsole from Zac

## Slide 3: Difficulties encountered during the week (What I did not do and why)
Documentation is a bit unorganized
ADMIN Access to computers

## Slide 4: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Learn Libero/Softconsole | 05/17 | 2
UART | 06/07 | 11
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 

## Slide 5: How can we help you achieve your goals?
Admin Access on STC159L01 and 2?

## Slide 6
Notes: Taken from Elder Bednar’s address: http://www2.byui.edu/Presentations/Transcripts/Devotionals/2006_10_31_Bednar.htm

## Slide 7: Week 4 (28-Apr to 4-May) Jonah Boe
Goal/Task | % Done | Hours (Act.)
Order tools and parts in order to solder the board | 90% | 1.5
Obtain a reflow oven, heat gun, and micro camera for soldering | 100% | 0.5
Review schematic for errors (includes determining the origin of the reference schematics used in the design.) | 30% | 6
Hours on task during the week (On track ≥ 13 / wk) | 13
Total hours on task so far this semester (On track ≥ 26 hrs) | 27.1

## Slide 8: Progress made during the week (Log) (What I did)
I got a substantial amount done getting the right tools for the job (some to keep, some on group card). Researched the proper reflow profiles for the solder past being used. Found a good solder masking product to put between pads under the FPGA connecter. This masking is silicone based, but has a much higher melting point than the solder past purchased by the last group. Studied the schematics handed to us for errors.

## Slide 9: Difficulties encountered during the week (What I did not do and why)
Found more errors on the PCB
Had planned to finish reviewing schematics, want to give it more attention
Have had some difficulty sourcing parts so they get here sooner than later

## Slide 10: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Finish reviewing schematic for problems and errors. | May 07, 2020 | 4
Solder the PCB | May 18, 2020 | 5
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 14

## Slide 11: How can we help you achieve your goals?
Review the schematics for errors as well. I would hope everyone would review them as apposed to breaking it up.

## Slide 12
Notes: Taken from Elder Bednar’s address: http://www2.byui.edu/Presentations/Transcripts/Devotionals/2006_10_31_Bednar.htm

## Slide 13: Week 4 (28-Apr to 4-May) Spencer Cheney
Goal/Task | % Done | Hours (Act.)
Learn VHDL | 50% | 3
Review UART Communication | 100% | 2
Got familiar with Softconsole and Libero | 75% | 2
Start working on developing UART Communication for FPGA | 20% | 2.5
Hours on task during the week (On track ≥ 13 / wk) | 10.5
Total hours on task so far this semester (On track ≥ 26 hrs) | 22.5

## Slide 14: Progress made during the week (Log) (What I did)
Develop basic UART design
Started to understand the file structure of the project
Work with Zac to understand what aspects of UART still need to be developed.

## Slide 15: Difficulties encountered during the week (What I did not do and why)
Struggles working with Libero
  We need admin priviledges to get it to work
Don't really understand file structure

## Slide 16: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Understand project structure and find out what everything is and where to start developing UART | 5/11 | 2
Work on adapting current UART functionality and examples to work with PCB pins and LCD screen | 5/25 | 4
Look through the VHDL code from the previous team | 5/18 | 5
Understand how to work with Libero software | 5/11 | 2
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 17: How can we help you achieve your goals?
Give us admin priviledges on Lab Computers

## Slide 18
Notes: Taken from Elder Bednar’s address: http://www2.byui.edu/Presentations/Transcripts/Devotionals/2006_10_31_Bednar.htm

## Slide 19: Week 4 (28-Apr to 4-May) Kyle Tolliver
Goal/Task | % Done | Hours (Act.)
Class / Coursework Including WIGS, Meeting, Peer Review and Leadership | 100 | 9
Previous Work/ OneDrive | 60 | 3.25
Set up VPN | 100 | .25
Arduino - Test | 100 | .5
Hours on task during the week (On track ≥ 13 / wk) | 13
Total hours on task so far this semester (On track ≥ 26 hrs) | 25

## Slide 20: Progress made during the week (Log) (What I did)
For example: Resources found (links, manuals), Designs created, Decisions made and corresponding rational, Photos of prototype progress, etc.
Condensed last semester's work
  Now about 2.5 GB
Reviewed last semester's work

## Slide 21: Difficulties encountered during the week (What I did not do and why)
Libero is confusing
Don't know VHDL

## Slide 22: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Learn Libero/Soft console | May 19 | 4
Class/Coursework -- Leadership, WIGS and Peer Review | May 12 | 8
Arduino COM | May 19 | 4
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 16

## Slide 23: How can we help you achieve your goals?
Hints for Libero and Soft console
Ideas for Arduino Com test
Get admin access to Lab computer 01

## Slide 24
Notes: Taken from Elder Bednar’s address: http://www2.byui.edu/Presentations/Transcripts/Devotionals/2006_10_31_Bednar.htm