## Project Tasks
Task | People Assigned | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | Flags
|  | 2020-04-26 | 2020-05-03 | 2020-05-10 | 2020-05-17 | 2020-05-24 | 2020-05-31 | 2020-06-07 | 2020-06-14 | 2020-06-21 | 2020-06-28 | 2020-07-05 | 2020-07-12 | 2020-07-19 | g = Group | Done, Dire | Set semester dates (Past weeks will be grayed out)
|  | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Thu
PCB | [14 empty] | g |  | "." = Work on task
Research PCB SMT Assembly | Jonah | [14 empty] | done | dire = Task is urgent | bar: 2020-04-26 to 2020-05-03
Assemble PCB | Jonah | [14 empty] | done | done = Task is complete | bar: 2020-05-03 to 2020-05-17
COMM | [14 empty] | g
Arduino Code for SPI/I2C/UART | Kyle | [14 empty] | done | bar: 2020-05-03 to 2020-06-14
Test PWM (Extra) | [15 empty] | +
10 Full-DuplexUART (Using Hamming Code and FIFOs) (Libero) | Spencer, Chris | [14 empty] | done | bar: 2020-05-10 to 2020-06-21
LCD Interface | Chris | [14 empty] | dire | bar: 2020-06-21 to 2020-06-28
LEARNING | [14 empty] | g
SoftConsole | All | [14 empty] | done | bar: 2020-05-03 to 2020-05-17
Libero | All | [14 empty] | done | bar: 2020-05-03 to 2020-05-17
TMR/CPU | [14 empty] | g
RISC-V TMR | Jonah | [14 empty] | dire | bar: 2020-05-17 to 2020-06-14
Implement RISC-V cores with varying configurations | Spencer | bar: 2020-05-31 to 2020-07-05
TESTING | [14 empty] | g
Write code to test system & peripherals | Kyle | bar: 2020-05-03 to 2020-06-28
SoftConsole Driver Modules | - | [14 empty] | done | bar: 2020-06-14 to 2020-06-21
GPIO | Chris, Jonah | [14 empty] | dire | bar: 2020-06-14
LCD Display | Chris, Jonah | [14 empty] | dire | bar: 2020-05-17 to 2020-06-21
SPI | Kyle | [14 empty] | done | bar: 2020-06-14
I2C | Kyle | [14 empty] | done | bar: 2020-06-14
LVDS UART | Spencer | [14 empty] | dire | bar: 2020-06-14 to 2020-07-05
Run Standard CPU Benchmarks | Kyle, Chris | [14 empty] | dire | bar: 2020-07-05
Determine Ideal RISC-V Configuration | Spencer, Jonah | bar: 2020-06-14 to 2020-07-05
DELIVERIES | ALL | [13 empty] | g
Webpage/Poster | Kyle | [14 empty] | dire | bar: 2020-06-21 to 2020-07-12
Presentation | ALL | [14 empty] | dire | Thursday July 16th | bar: 2020-07-12
Demonstration & Oral Report | Jonah,Spencer | [14 empty] | dire | bar: 2020-07-12
Final Report | ALL | [14 empty] | dire | Monday July 13th | bar: 2020-07-12 to 2020-07-19
NASA Form | Jonah,Spencer | [14 empty] | dire | bar: 2020-07-19
Ship Equipment To Randy | ALL- in Rexburg | [14 empty] | dire | bar: 2020-07-19
Pre-Project Review | [14 empty] | g
Check Schematics for Accuracy | Jonah,Chris | [14 empty] | Done | bar: 2020-05-03 to 2020-05-17
Check PCB for accuracy (Workable) | Jonah,Chris | [14 empty] | Done | bar: 2020-05-03 to 2020-05-17

## W20
Project Name:
Task | People Assigned | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | Flags
|  | 2020-01-12 | 2020-01-19 | 2020-01-26 | 2020-02-02 | 2020-02-09 | 2020-02-16 | 2020-02-23 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2020-03-22 | 2020-03-29 | 2020-04-06 | g = Group | Done, Dire | Set semester dates (Past weeks will be grayed out)
|  | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Thu
PCB | [14 empty] | g |  | "." = Work on task
Design Multi-Channel ADC Circuit | Max | [14 empty] | Done | dire = Task is urgent | bar: 2020-01-26 to 2020-02-16
LEDs (some RGB), Switches, GPIO Headers | James | [14 empty] | Done | done = Task is complete | bar: 2020-01-26 to 2020-02-16
SPI & I2C Ports | James | [14 empty] | Done | bar: 2020-01-26 to 2020-02-16
Accelerometer, Temperature and Humidity Sensor | Zac | [14 empty] | Done | bar: 2020-01-26 to 2020-02-09
Heartrate Sensor, Pressure Sensor | Sam | [14 empty] | Done | bar: 2020-01-26 to 2020-02-16
LCD Screen Interface (like the NHD-C0216CZ-FSW-FBW-3v3) | Michael | [14 empty] | Done | bar: 2020-01-26 to 2020-02-16
UART Connector (50 pin) | James | [14 empty] | Done | bar: 2020-01-26 to 2020-02-16
Design PCB Layout | Max, Sam, James | [14 empty] | Done | bar: 2020-02-09 to 2020-03-08
Assemble PCB | Max, Sam, James | bar: 2020-03-01 to 2020-03-15
COMM | [14 empty] | g
10 Full-DuplexUART (Using Hamming Code and FIFOs) | James | [15 empty] | Waiting for implementation | bar: 2020-02-16 to 2020-03-08
SPI | Max | [14 empty] | Done | Waiting for implementation | bar: 2020-01-26 to 2020-02-16
I2C | Sam | [14 empty] | Done | Waiting for implementation | bar: 2020-01-12 to 2020-04-06
PWM | Zac | [14 empty] | Done | bar: 2020-02-09 to 2020-02-23
TMR/CPU | [14 empty] | g
Implement RISC-V cores with varying configurations | Michael, Zac | bar: 2020-02-02 to 2020-03-15
RISC-V TMR | Michael, Zac | [14 empty] | Done-ish | bar: 2020-02-09 to 2020-03-01; 2020-03-15 to 2020-03-29
FRAM TMR | Michael, Zac | [15 empty] | Lowest Priority | bar: 2020-02-09 to 2020-03-08
TESTING | [14 empty] | g
Write code to test system & peripherals | ALL | bar: 2020-03-08 to 2020-03-29
Run Standard CPU Benchmarks | ALL | bar: 2020-02-23 to 2020-03-29
Determine Ideal RISC-V Configuration | ALL | bar: 2020-03-22 to 2020-03-29
DELIVERIES | [14 empty] | g
Poster | bar: 2020-04-06
Demonstration & Oral Report | bar: 2020-04-06
Final Report | bar: 2020-03-29 to 2020-04-06